## Description
COMP 5700/6700/6706 -- Software Process
Assignment: | Assignment 2
Objective: | To gain experience with TDD
Product: | Write software to model a solved Rubik's cube.
Deliverables: | Via Canvas: | Include this spreadsheet with completed process information with your Canvas submission.]
| Via GitHub: | Push your code to GitHub Classroom
Notes on Process: | - Follow the process in the "Process" worksheet for this assignment.
- This homework assignment is be accomplished individually
- Ensure you follow the course coding and counting standards.
- Be honest in your data. Your grade depends on how you follow the process and the quality of your work, not on the speed of your work or the number of defects found.
- Below are clarifications for process worksheets that have been problematic in the past:
|  | Worksheet | Special Instructions
|  | Plan | Record lines of code for production code only. Do not include test code.
|  | Acceptance | Develop acceptance tests for the specified black box. Do not include tests for items that are not part of the specifications (meaning, items over and above the specs -- these tests will appear in your individual unit test files). Write the expected results at planning time. Modify if necessary later. Don’t write actual results in advance.
|  | Time Log | Use the "sandbox" activity to record time spent experimenting with the assignment requirements.
|  | Change Log | The "Reference to a Previous Change" column allows you to indicate that you are fixing a fix. The value in the column should be the number on the change log of the fix you are repairing.
|  | Historical Data | Record your process and product data from all previous programming assignments. Do this as part of the planning activity.
|  | Review | During the planning activity, list a count of all defects that you've previously encountered. Construct a checklist from your defect logs. Indicate during the review activity the number of times the review checklist item found an error.
|  | Scenarios | Create an interface specification depicting the interaction between a test driver and the class specified above. Create nominal scenario(s) and anomalous scenario(s) sufficient to convey your understanding of software behavior
|  | Lessons Learned | This tab is optional. Use it to record great ideas, suggestions, etc. Whining is not productive :)
|  | Architecture | Develop CRC cards only for the production code needed to implement the specifications. Do not include CRC cards for test drivers.
|  | Estimate | Record all the items from your architecture. Do not include test code.
|  | Iterations | Record the number of iterations you plan to use, together with the planned velocity of each iteration. Record the amount of time you plan to have available each day of the project window. Please plan for more than one iteration.
Special Instructions: | - Selected cells in this spreadsheet are locked against inadvertent editing. Should you need to unlock the spreadsheet, select the protected worksheet, select Tools -> Protection -> unprotect.

## Process
Constants |  |  |  | Assignment 2
Start date: | 36526 |  | Grades: | 1
End date: | 73051 |  |  | 0.95
Phases: | Analysis |  |  | 0.9
| Architecture |  |  | 0.85
| Project planning |  |  | 0.8
| Interation planning |  |  | 0.75
| Construction |  |  | 0.7
| Refactoring |  |  | 0.65
| Review |  |  | 0.5
Integration test
Repatterning
Postmortem
Sandbox
Defect Types: | Requirements Change | Changes to requirements | Iteration | did not follow
| Requirements Clarification | Clarifications to requirements |  | very painful
| Product syntax | Syntax flaws in the deliverable product |  | painful
| Product logic | Logic flaws in the deliverable product |  | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | very helpful
| Test syntax | Syntax flaws in the test code
| Test logic | Logic flaws in the test code
| Test interface | Flaws in the interface of a component of the test code
| Test checking | Flaws with boundary/type checking within a component of the test code
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 0
Y/N: | Yes |  |  | 0
| No |  |  | 0
Proxy Types: | -
Calculation
Data
I/O
Logic
Sizes: | VS | S | M | VL
upper | -1.5 | -0.5 | 0.5 | 99999
mid | -2 | -1 | 0 | 2
lower | 0 | -1.5 | -0.5 | 1.5
| 0 | 0 | 0
<-- Mandatory |  | ✔
Process Script
Minimal Guiding Indicators |  |  |  | Minimal Sufficient Activities
| Goal | Indicator |  |  | Engineering Activities
| Cost: | None |  |  | Envision
| Schedule: | On time |  |  | Analyze
| Performance: |  |  |  | Synthesize
| Product: |  |  |  | Architecture
| NFR: | None |  |  | Articulate
| FR: | Equivalence Class Partitioning |  |  | Construct
| Process: | Completed spreadsheet |  |  | Interpret
Integration Test
Operational Activities
Plan
Plan project
Monitor/Control
Post Mortem
Release
Minimal Viable Process |  |  |  | Minimal Effective Practices
|  |  |  | MSA | MEP | Spreadsheet tab on which to document MEP:
|  |  |  | Plan Project | • Write as many acceptance tests as you feel are necessary to understand the assignment | Acceptance
[5 empty] | • Guess projected production code LOC | Plan
[5 empty] | • Guess projected effort (in minutes) | Plan
|  |  |  | Construction | • repeat
• • select/write a test case and run it as a red light test
• • while the test is not red
• • • diagnose why the test was not red
• • • if the problem was due to incorrect test code
[5 empty] | • • • • fix the defect and log it in the change log | Change Log
• • • else
• • • • continue to the next red light test
• • build enough production code to make the test pass
• • run the test as a green light test
• • while the test is not green
[5 empty] | • • • fix the defect and log it in the change log | Change Log
• • • run the test as a green light test
• • clean up the code as appropriate
• until test coverage is sufficient and all tests pass
• Commit all code to git
|  |  |  | Post Mortem | • Record acceptance test results | Acceptance
[5 empty] | • Count production LOC | Plan
[5 empty] | • Record lessons learned (optional) | Lessons
|  |  |  | Release | • Commit spreadsheet to git
• Commit all code to git
• Push to GitHub.com
• Submit GitHub account name to Canvas
|  |  |  | Monitor | • Record time spent in each activity. | Time Log
[5 empty] | • Record defects, changes to requirements. | Change Log
Minimal Guiding Indicators
Cost: |  | -
Schedule: |  | Submitted on time
Performance:
Product:
| NFR: | Meets delivery requirements.
| FR: | Boundary Value Analysis
| Process: | Evident on spreadsheet
Operational Engineering
Project Planning
Post Mortem
Release
Monitor/Cntrl
Construct
Not all components are constructed

## Customer Needs
Conversation with the customer:
Client Clarification:
The production code must contain, at a minimum, the components listed below:
dispatch … provided to you as a partially-completed function
You are free to implement additional classes and methods.
Specifications
Background: | We are building a software representation of Rubik's Cube (see https://en.wikipedia.org/wiki/Rubik%27s_Cube for background on the cube).
Our implementation will ultimately consist of microservices that manipulate Rubik's cube. Each individual microservice performs a specific cube function. When a microservice is passed information about the current state of the cube, it carries out its function and outputs a new cube state. The microservices serve as middleware, meaning, it operates without a user interface, and is triggered by an HTTP request. Information is carried to the microservice via a URL query string; the microservice returns information via an HTTP response. You will get some details in this assignment, with other details being explained incrementally in subsequent assignments.
This assignment asks you to write a microservice that returns a model of a solved Rubik's Cube.
Functional Specifications: | def dispatch
|  | Abstraction: | dispatch performs a specific game function based on information it receives.
| method |  | description
|  | dispatch | dispatch(parm)
Performs the function specified by the "op" value passed as one of the input elements.
Invocation Prototype:
|  |  | Parameters: | parm is a python dictionary consisting of name-value pairs representing the query string portion of the URL. Mandatory. Arrives validated.
|  |  | Desired behavior (normal): | Performs the function named by the value of the 'op' dictionary key. Returns a python dictionary that represents the resulting state.
|  |  |  | Operation Name | Operation Description
|  |  |  | '{"op": "create"}' | Carries out the "create" operation
A description of each operation is given in the "operation" section below.
|  |  | Desired behavior (errors): | If: | • parm does not contain 'op' as a name-value pair
|  |  |  | Action: | Return a python dictionary containing the key "status" having the value "error: xxx", where xxx is a meaningful diagnostic.
|  |  |  | Exit conditions: | No further processing takes place once an error is discovered.
|  |  | State change: | No state is retained or changed.
|  |  | General examples: | Valid (Input is represented as an abbreviated URL; output is represented as a python dictionary)
|  |  |  | Input: | http:// ... /rcube?op=xxx
|  |  |  | Returns: | A python dictionary resulting from the 'xxx' operaiton
Invalid (Input is represented as an abbreviated URL; output is represented as a python dictionary)
|  |  |  | Input: | http:// ... /rcube?key=value
|  |  |  | Returns: | {'status': 'error: op code is missing'}
|  |  |  | Input: | http:// ... /rcube
|  |  |  | Returns: | {'status': 'error: op code is missing'}
|  |  |  | Input: | http:// ... /rcube?
|  |  |  | Returns: | {'status': 'error: op code is missing'}
|  |  | Implementation note: | Server interface code parses the HTTP request query string into a python dictionary, passes the dictionary to dispatch(), then coverts the results of dispatch() to a string that is returned as the HTTP response. You should not have to modify this code. Provided to you is a skeletal version of dispatch(), which will require your modification.
| operation |  | description
'{"op": "create"}'
Creates a solved cube of a specified size.
|  |  | Relevant dictionary elements: | "f" | Specifies the color of the front side of the cube. It is a string of length .GT. 0. Optional. Defaults to "green" if missing. Arrives unvalidated.
|  |  |  | "r" | Specifies the color of the right side of the cube. It is a string of length .GT. 0. Optional. Defaults to "yellow" if missing. Arrives unvalidated.
|  |  |  | "b" | Specifies the color of the back side of the cube. It is a string of length .GT. 0. Optional. Defaults to "blue" if missing. Arrives unvalidated.
|  |  |  | "l" | Specifies the color of the top side of the cube. It is a string of length .GT. 0. Optional. Defaults to "white" if missing. Arrives unvalidated.
|  |  |  | "t" | Specifies the color of the under side of the cube. It is a string of length .GT. 0. Optional. Defaults to "red" if missing. Arrives unvalidated.
|  |  |  | "u" | Specifies the color of the front of the cube. It is a string of length .GT. 0. Optional. Defaults to "orange" if missing. Arrives unvalidated.
Dictionary elements not specified above are ignored.
|  |  | Desired behavior (normal): | Returns a dictionary consisting of the the following key-value pairs:
"cube" models the physical Rubik's cube. It is the key whose value describes the six faces of the cube. The value is a list having exactly 54 strings. The first 9 strings represent the elements on the front face, the second 9 strings represent the elements on the right face, and so forth for the back, left, top, and under faces, respectively. Each face's elemen ts are arranged in row-major order, beginning with the upper left corner. The "Support Info" tab illustrates the layout of the cube.
"status" is a key-value pair whose value is the string, "created".
|  |  | Desired behavior (errors): | If: | any dictionary element violates the description above
|  |  |  | Action: | Return a dictionary consisting soley of the "status" key having a value of "error: xxx", where xxx is a meaningful diagnostic.
|  |  |  | Exit conditions: | No further processing takes place once an error is discovered.
|  |  |  | If: | any face does not have a unique color
|  |  |  | Action: | Return a dictionary consisting soley of the "status" key having a value of "error: xxx", where xxx is a meaningful diagnostic.
|  |  |  | Exit conditions: | No further processing takes place once an error is discovered.
|  |  | Specific examples: | Valid (Input is represented as an abbreviated URL; output is represented as a python dictionary)
|  |  |  | Input: | http:// ... /rcube?op=create
|  |  |  | Sample return: | {'status': 'created', 'cube': ['green', 'green', 'green', 'green', 'green', 'green', 'green', 'green', 'green', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange']}
|  |  |  | Input: | http:// ... /rcube?op=create&r=r&l=l&t=t&u=u&f=f& b=b
|  |  |  | Sample return: | {'status': 'created', 'cube': ['f', 'f', 'f', 'f', 'f', 'f', 'f', 'f', 'f', 'r', 'r', 'r', 'r', 'r', 'r', 'r', 'r', 'r', 'b', 'b', 'b', 'b', 'b', 'b', 'b', 'b', 'b', 'l', 'l', 'l', 'l', 'l', 'l', 'l', 'l', 'l', 't', 't', 't', 't', 't', 't', 't', 't', 't', 'u', 'u', 'u', 'u', 'u', 'u', 'u', 'u', 'u', 'u',]}
|  |  |  | Input: | http:// ... /rcube?op=create&f=f&r=r&b=b&l=l&t=1
|  |  |  | Sample return: | {'status': 'created', 'cube': ['f', 'f', 'f', 'f', 'f', 'f', 'f', 'f', 'f', 'r', 'r', 'r', 'r', 'r', 'r', 'r', 'r', 'r', 'b', 'b', 'b', 'b', 'b', 'b', 'b', 'b', 'b', 'l', 'l', 'l', 'l', 'l', 'l', 'l', 'l', 'l', '1', '1', '1', '1', '1', '1', '1', '1', '1', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange']}
|  |  |  | Input: | http:// ... /rcube?op=create&f=f&r=r&b=b&l=l&t=1&under=42
|  |  |  | Sample return: | {'status': 'created', 'cube': ['f', 'f', 'f', 'f', 'f', 'f', 'f', 'f', 'f', 'r', 'r', 'r', 'r', 'r', 'r', 'r', 'r', 'r', 'b', 'b', 'b', 'b', 'b', 'b', 'b', 'b', 'b', 'l', 'l', 'l', 'l', 'l', 'l', 'l', 'l', 'l', '1', '1', '1', '1', '1', '1', '1', '1', '1', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange']}
Invalid (Input is represented as an abbreviated URL; output is represented as a python dictionary)
|  |  |  | Input: | http:// ... /rcube?op=create&f=red&u=red
|  |  |  | Sample return: | {'status': 'error: at least two faces have the same color'}
http://umphrda-rcube.mybluemix.net/rcube?op=create&f=red
URL of microservice provider
Name of the microservice
Parameters passed to the microservice. These will be provided to you as a Python dictionary: {'f': 'red', 'op': 'create'}

## Spec Notes (hidden)
Specification Notes

## Support Info
2D illustration of a 3D cube.
The cube we are modeling has 6 faces, with each face consisting of 9 elements arranged in a 3 x 3 matrix. | [5 empty] | top-1 | top-2 | top-3 |  | back-1 | back-2 | back-3
Faces are highlighted with a bold border. The name of each face is indicated, along with the row-major ordering of the face elements. |  |  |  |  | top-4 | top-5 | top-6 |  | right-3 | back-4 | back-5 | back-6
More info: | https://rubiks-cube-solver.com/ |  |  | top-7 | top-8 | top-9 | right-1 | right-2 | right-6 | back-7 | back-8 | back-9
| left-1 | left-2 | left-3 | top-7: front-1; top-8: front-2; top-9: front-3; right-2: right-5; right-6: right-9
| left-4 | left-5 | left-6 | top-7: front-4; top-8: front-5; top-9: front-6; right-1: right-4; right-2: right-8
| left-7 | left-8 | left-9 | top-7: front-7; top-8: front-8; top-9: front-9; right-1: right-7
|  |  |  | under-1 | under-2 | under-3
|  |  |  | under-4 | under-5 | under-6
|  |  |  | under-7 | under-8 | under-9

## Assessment
Constants |  |  |  |  | Assignment 2
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analysis |  |  | AB | 0.9
| Architecture |  |  | B | 0.85
| Project planning |  |  | BC | 0.8
| Interation planning |  |  | C | 0.75
| Construction |  |  | CD | 0.7
| Refactoring |  |  | D | 0.65
| Review |  |  | F | 0.5
Integration test
Repatterning
Postmortem
Sandbox
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed
| Calculation |  |  | Not tested
| Data |  |  | Not applicable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Assessment Worksheet
Name: |  | Turner Atwood
User name: |  | bta0008
GitHub user name: |  | bta0008
URL of microservice:
Instructor Assessment
Product Assessment
Process Assessment:
Score: |  | out of | 100
Grading rubric: Product Aspect
| AA | 100 | Exceptional job worthy of being used as an example of superior work
| A | 95 | Product satisfies all functional requirements, has insignificant nonfunctional requirement nonconformance
| AB | 90 | Product satisfies all functional requirements, has minor nonfunctional requiement nonconformance
| B | 85 | Product satisfies all functional requirements, has major nonfunctional requirement noncomformance
| BC | 80 | Product encounters minor functional deviations, has insignificant nonfunctional requirement nonconfirmance
| C | 75 | Product encounters minor functional deviations, has minor nonfunctional requirement nonconfirmance
| CD | 70 | Product encounters minor functional deviations, has major nonfunctional requirement nonconfirmance
| D | 65 | Product encounters multiple significant problems in functional and nonfunctional requirements
| F | 50 | Deliverables show lack of comprehension of concepts, or are incomplete
Grading rubic: Process Aspect
| AA | 100 | Exceptional job worthy of being used as an example of superior work
| A | 95 | Process has insignificant exceptions
| AB | 90 | Process has multiple minor exceptions
| B | 85 | Process has exceptions that obsure activity verification
| BC | 80 | Process has exceptions with historical data that affect the current project
| C | 75 | Process has exceptions that suggest lack of comprehension of concepts
| CD | 70 | Process has exceptions that bring into question the validity of the data
| D | 65 | Process has exceptions suggesting it wasn't followed.
| F | 50 | Deliverables are incomplete
Quality checks
General
Are all regions highlighted in yellow appropriately complete?
Does the workbook reflect a faithful record of information?
Has this assignment been uploaded as specified by the assignment description?
Project Plan Summary
Was the planned information determined before development and not altered after development?
Is planned time expressed in minutes?
Do LOC counts address production code (and exclude test code)?
Is the actual line count calculated according to the counting standard?
Time Recording Log
Does the log reflect a faithful record of time spent?
Do no times span midnight?
Does the log reflect the activities in the specified process?
Is post mortem the final phase?
Does the time recording log reflect the your lifecycle?
Change Log
Is each change accompanied by a description in the "comment" field?
Are changes recorded against the appropriate phase in which they were injected and removed?
Does the "removed" count equal the "injected" count? If not, is the rational documented in the "lessons learned" tab?
Are the dates and times in the change log consistent with the dates and times in the time recording log?
Acceptance Report
Were initial "expected results" determined before coding began?
Are the expected results sufficiently detailed for an independent party to test the software?
Are the expected results correct?
Do actual results support expected results?
Do actual results marked as "Passed with issues" include a comment?
Are acceptance tests written to the level of boundary value analysis?
Source Code
Does the code reflect the coding standard?
Will the code compile without change?
Does the production code contain any packages that aren't part of the customer's production environment.
Does the code take into consideration specified error conditions?
Does the code fulfill the assignment requirements?
Does the code follow the prescribed directory format (i.e., prod, test, sandbox)?
Historical Data
Is the historical data complete?
Have previously noted problems in process measurements been corrected?
Deliverables
Has the spreadsheet been pushed to GitHub?
Has all the code been pushed to GitHub?
Is test code in a separate folder?
Will the test code work without modification?
Does the git respository reflect commits at the specified process points?
Does the "Assessment" tab include your name, your AU username, etc.
Review
Did you construct your review checklist during the planning phase?
Does the error count indicated the analysis of defects match your historical defect count?
Are checklist items answerable in "yes" or "no" terms?
Does your checklist reflect at least two common items from your defect log ?
Does your checklist contain more than "mom and apple pie" items?
Refactor
Is code free of the following bad smells: duplicate code, long methods, long classes
temporary variables, useless comments, coding standard violations?
Scenario
Were the scenarios constructed during the analysis phase (and not changed later)?
Does each scenario describe as fully as possible the interaction with the software under construction?
Are the actors correctly identified?
Are suitably understandable examples given?
Are events and responses directly observable?
Architecture
Was the architecture determined before construction (and not changed later)?
Does the architecture reflect a solid initial understanding of the solution?
Does the architecture show all components required for the solution (with the exception of system built-in components)?
Are collaborators specified correctly?
Do functionally-decomposed components have only one operation? Has the operation been given the component name?
Are component operations given names to suggest their behavior?
Does the architecture exhibit "good" design characteristics, such as appropriate levels of coupling, cohesion, etc.?
Estimate
Does each component denoted by a CRC card appear in the estimate as either base code, new components, or reused code?
Is base code vs reuse code identified correctly?
Do the base components and the new comopnents reflect the architecture?
Are the base components and new components sized according to historical proxies?
Is a rationale provided if either the LOCp and/or Ep are overridden?
Is actual LOC data recorded at post mortem time?
Iterations
Is more than one iteration planned?
Does the WBS list all iterations?
Is the overall estimate of time in the WBS consistent with the calculated effort?
Are the planned completion dates of iterations in the WBS consistent with the calendar?
Are planned times recorded from the start of the calendar through the end of the project?
Does the calendar corroborate the WBS, and visa versa?
Construction
Did you follow the design -> test(failure) -> code -> test(success) -> clean up (if necessary) -> repeat pattern?
Are all unit tests written so that passing the test satisifies requirements?
Are unit tests written to the level of boundary value analysis?
Is there at least one test suite which, when run, exercises the entire production code base?
Does your code pass all test cases?

## Historical Data (hidden)
Constants |  |  |  |  | Assignment 2
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analysis |  |  | AB | 0.9
| Architecture |  |  | B | 0.85
| Project planning |  |  | BC | 0.8
| Interation planning |  |  | C | 0.75
| Construction |  |  | CD | 0.7
| Refactoring |  |  | D | 0.65
| Review |  |  | F | 0.5
Integration test
Repatterning
Postmortem
Sandbox
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed
| Calculation |  |  | Not tested
| Data |  |  | Not applicable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
Historical Data
Current Assignment: |  | Assignment 6 | CAAssignment 6.xls
Immediate Past Assignment: |  | Assignment 4 | Assignment 4
Project Plan Summary From |  |  | Assignment 4
Program Size (LOC) |  | Plan | Actual | Actual to Date
Base code LOC count
Lines deleted from Base
Lines modified from Base
Lines added to Base
Reused lines
New lines of production code
Component Count |  | Plan | Actual | Actual to Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
Time In Phase (minutes) |  | Plan | Actual | Actual To Date | Actual to Date %
Analysis |  |  | 0 | 0 | 0%
Architecture |  |  | 0 | 0 | 0%
Project planning |  |  | 0 | 0 | 0%
Interation planning |  |  | 0 | 0 | 0%
Construction |  |  | 0 | 0 | 0%
Refactoring |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repatterning |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  | 0 | 0 | 0 | 0%
Changes traced to |  |  |  | Actual to Date | Actual to Date %
Analysis |  |  |  | 0 | 0%
Architecture |  |  |  | 0 | 0%
Project planning |  |  |  | 0 | 0%
Interation planning |  |  |  | 0 | 0%
Construction |  |  |  | 0 | 0%
Refactoring |  |  |  | 0 | 0%
Review |  |  |  | 0 | 0%
Integration test |  |  |  | 0 | 0%
Repatterning |  |  |  | 0 | 0%
Postmortem |  |  |  | 0 | 0%
Sandbox |  |  |  | 0 | 0%
TOTAL |  |  |  | 0 | 0%
Changes implemented in |  |  |  | Actual to Date | Actual to Date %
Analysis |  |  |  | 0 | 0%
Architecture |  |  |  | 0 | 0%
Project planning |  |  |  | 0 | 0%
Interation planning |  |  |  | 0 | 0%
Construction |  |  |  | 0 | 0%
Refactoring |  |  |  | 0 | 0%
Review |  |  |  | 0 | 0%
Integration test |  |  |  | 0 | 0%
Repatterning |  |  |  | 0 | 0%
Postmortem |  |  |  | 0 | 0%
Sandbox |  |  |  | 0 | 0%
TOTAL |  |  |  | 0 | 0%
Size Matrix (LOC/Method)
| VS | S | M | L | VL
Upper | 1 | 1 | 1 | 1 | big
Mid | 1 | 1 | 1 | 1 | 1
Lower | 0 | 1 | 1 | 1 | 1
| VS | S | M | L | VL
Project History
| New and Changed LOC |  |  | Effort
Project Name | Raw LOC | Planned LOC | Actual LOC | Estimated Time | Actual Time | LOCa/LOCr | Ea/LOCa
1.xls | 0 |  |  |  |  | 0 | 0
CA02 | 0 |  |  |  |  | 0 | 0
3.xls | [5 empty] | 0 | 0
CA04 | 0 |  |  |  |  | 0 | 0
CA05 |  | 0 | 0 | 0 | 0 | 0 | 0
Project Trends
Productivity= |  | LOC/hr
Average size= |  | LOC/method
Component History
Component Name |  | Total LOC | Method Count | Type | Size | LOC/method | ln(LOC/meth)
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | - |  |  | `
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
|  |  |  | - | -
[6 empty] | Average= | 0
[6 empty] | Std= | 0
Note on C52: Estimate of the number of lines deleted from previously-written code
Note on C53: Estimated of the number of lines modified from previously-written code
Note on C54: Estimate of the number of lines added to previously-written code to bring it to the point where new functionality can be added
Note on C55: Count of the number of lines of reused source code
Note on C56: Estimate the number of new lines of code that provide new functionality to meet the specifications of this assignment.
Note on C60: Estimate of the number of previously-written components that require modification
Note on C61: Estimate of the number of entirely new components

## Review (hidden)
Review
Standards
Start date: | 2000-01-01 |  | Grades: |  |  | AA
End date: | 2020-01-01 |  |  |  |  | A
Phases: | Analysis |  |  |  |  | AB
| Architecture |  |  |  |  | B
| Planning |  |  |  |  | BC
| Construction |  |  |  |  | C
| Refactoring |  |  |  |  | CD
| Review |  |  |  |  | D
| Integration Test |  |  |  |  | F
Postmortem
Sandbox
Defect Types: | Documentation |  | Iteration |  |  | NA
| Build |  |  |  |  | 1
| Product syntax |  |  |  |  | 2
| Product logic |  |  |  |  | 3
| Product interface |  |  |  |  | 4
| Product checking |  |  |  |  | 5
| Test syntax |  |  |  |  | 6
| Test logic |  |  |  |  | 7
| Test interface |  |  |  |  | 8
| Test checking |  |  |  |  | 9
| Bad Smell |  |  |  |  | 10
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Sizes: | VS
S
M
L
VL
Defect Pareto Analysis (taken from all defects to date)
| Type | Description |  | Count of Occurrences | %
| Documentation | #REF!
| Build | #REF!
| Product syntax | #REF!
| Product logic | #REF!
| Product interface | #REF!
| Product checking | #REF!
| Test syntax | #REF!
| Test logic | #REF!
| Test interface | #REF!
| Test checking | #REF!
| Bad Smell | #REF!
|  |  | Total | 0 | 0%
Code Review Checklist
| Item |  |  | Number of times this item detected a defect during review

## Acceptance
Constants |  |  |  |  | Assignment 2
Start date: | 36526 |  | Grades: | AA | 1 | 0
End date: | 73051 |  |  | A | 0.95 | 0
Phases: | Analysis |  |  | AB | 0.9 | 0
| Architecture |  |  | B | 0.85 | 0
| Project planning |  |  | BC | 0.8 | 0
| Interation planning |  |  | C | 0.75 | 0
| Construction |  |  | CD | 0.7 | 43360
| Refactoring |  |  | D | 0.65 | 43361
| Review |  |  | F | 0.5 | 43362
| Integration test |  |  |  |  | 43363
| Repatterning |  |  |  |  | 43364
| Postmortem |  |  |  |  | 43365
| Sandbox |  |  |  |  | 43366
43367
43368
43369
#REF!
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | #REF!
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | #REF!
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | #REF!
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | #REF!
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | #REF!
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | #REF!
| Test syntax | Syntax flaws in the test code |  | 6 |  | #REF!
| Test logic | Logic flaws in the test code |  | 7 |  | #REF!
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | #REF!
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | #REF!
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | #REF!
Y/N: | Yes |  |  | Passed | 0 | #REF!
| No |  |  | Passed with issues | 0 | 43383
Proxy Types: | - |  |  | Failed |  | 43384
| Calculation |  |  | Not tested |  | 43385
| Data |  |  | Not applicable |  | 43386
| I/O |  |  |  |  | 43387
| Logic |  |  |  |  | 43388
43389
Sizes: | VS | S | M | L | VL | 0
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | 0
mid | -2 | -1 | 0 | 1 | 2 | 0
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | 0
| 0 | 0 | 0 | 0 |  | 0
Acceptance Test Report
Use this worksheet to record tests that, if passed, tell you that your software is complete. It is not a chronology, so do not list a history of tests. List only tests that are directly linked to requirements (in other words, do not list tests for methods or components that you create over and above what is required to fulfill the specified interface definition -- these tests will appear in your individual unit test files). Write the expected results at planning time. Modify if necessary later. Don’t write actual results in advance.
Requirements:
dispatch
'{"op": "create"}'
Requirement | Test | Expected Results |  | Actual Results | Issues
'{"op": "create"}' | http:// ... /rcube?op=create | {'status': 'created', 'cube': ['green', 'green', 'green', 'green', 'green', 'green', 'green', 'green', 'green', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange']} |  | Passed
dispatch | http:// ... /rcube?op=create | {'status': 'created', 'cube': ['green', 'green', 'green', 'green', 'green', 'green', 'green', 'green', 'green', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange']} |  | Passed
dispatch | http:// ... /rcube? | {'status': 'error: missing op'} |  | Passed
dispatch | http:// ... /rcube?f=red | {'status': 'error: missing op'} |  | Passed
'{"op": "create"}' | Testing the creating of cubes with non-default faces: http:// ... /rcube?op=create&f=purple&r=black | {'status': 'created', 'cube': ['purple', 'purple', 'purple', 'purple', 'purple', 'purple', 'purple', 'purple', 'purple', 'black', 'black', 'black', 'black', 'black', 'black', 'black', 'black', 'black', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange']} |  | Passed
'{"op": "create"}' | Testing the swapping of default values for faces:http:// ... /rcube?op=create&f=orange&r=red&t=yellow&u=green | {'status': 'created', 'cube': ['orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'green', 'green', 'green', 'green', 'green', 'green', 'green', 'green', 'green']} |  | Passed
'{"op": "create"}' | Testing that colors are case-sensative: http:// ... /rcube?op=create&f=Yellow&b=White&l=white&t=WHITE&u=2179 | {'status': 'created', 'cube': ['Yellow', 'Yellow', 'Yellow', 'Yellow', 'Yellow', 'Yellow', 'Yellow', 'Yellow', 'Yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'White', 'White', 'White', 'White', 'White', 'White', 'White', 'White', 'White', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'WHITE', 'WHITE', 'WHITE', 'WHITE', 'WHITE', 'WHITE', 'WHITE', 'WHITE', 'WHITE', '2179', '2179', '2179', '2179', '2179', '2179', '2179', '2179', '2179']} |  | Passed
'{"op": "create"}' | Testing that invalid face keys are ignored http:// ... /rcube?op=create&f=purple&z=purple | {'status': 'created', 'cube': ['purple', 'purple', 'purple', 'purple', 'purple', 'purple', 'purple', 'purple', 'purple', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'yellow', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'blue', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'white', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'red', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange', 'orange']} |  | Passed
'{"op": "create"}' | Testing error on two non-unique colors: http:// ... /rcube?op=create&f=purple&r=purple | {'status': 'error: non-unique color(s) specified'} |  | Passed
'{"op": "create"}' | Testing error on three non-unique colors: http:// ... /rcube?op=create&r=purple&b=purple&l=purple | {'status': 'error: non-unique color(s) specified'} |  | Passed
'{"op": "create"}' | http:// ... /rcube?op=create&f=yellow | {'status': 'error: non-unique color(s) specified'} |  | Passed
Note on A55: Establish traceability between the tests and requirements.
Note on B55: Defines observable tests that have quantifiable resutls.
Note on C55: Specifies the result that that the test is anticipated to produce.
Note on E55: Defines the result of running the test in relation to the expected result.
Note on F55: Required whenthe actual result is "Passed with issues"; optional otherwise. An "issue" is a side-effect that is not part of the specified test.

## Map (hidden)
Sceneario-Component Map
X
Component Names:
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!

## Architecture (hidden)
Architecture
Use this worksheet to describe components required to implement the specifications. List new components and base components. Do not include extraneous components.
Standards
| Start date: | 2000-01-01
| End date: | 2010-01-01
| Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
| Defect Types: | Documentation
Syntax
Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
| Y/N: | Yes
No
| Component Types: | Calculation
Data
I/O
Logic
| Design Approaches: | Object-oriented
Functional
| Sizes: | VS
S
M
L
VL
| Duration: | LOCe x T
LOCa x T
Productivity
1 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
2 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
3 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
4 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
5 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
6 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
7 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
8 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
9 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
10 | Component Name:
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
11 | Component Name: | 0
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
12 | Component Name: | 0
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
13 | Component Name: | 0
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
14 | Component Name: | 0
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
15 | Component Name: | 0
Design Approach:
Parent Component:
Attributes (optional):
Component Type:
Collaborators:
Operations:
Note on B43: Identifying name for this design class or function.
Note on B44: Indicate if this design component will follow an object-oriented approach or a functional approach.
Note on B45: Superclass of this design component. Leave blank if no superclass.
Note on B46: Attributes (e.g., public fields, public constants) associated with this design component. OPTIONAL
Note on B47: Standard category of the design component.
Note on B48: List components that this component calls upon to fulfill its purpose.
Note on B49: Description of the operations of this design component. If your are taking an object-oriented approach, list the methods associated with this object in the "operation" column. If you are taking a functional approach, list the component name in the "operation" column. Note: an object-oriented approach may result in zero or more operations; a functional approach will have only one operation listed.

## Estimation (hidden)
Size Estimate
Standards
Start date: | 2000-01-01 |  |  | Grades: | AA
End date: | 2020-01-01 |  |  |  | A
Phases: | Planning |  |  |  | AB
| Architecture |  |  |  | B
| Construction |  |  |  | BC
| Refactoring |  |  |  | C
| Integration Test |  |  |  | CD
| Review |  |  |  | D
| Sandbox |  |  |  | F
Postmortem
Defect Types: | Documentation
| Build |  |  | Type | Event
| Product syntax |  |  |  | Response
| Product logic |  |  | Origin | Test Component
| Product interface |  |  |  | Blackbox
| Product checking |  |  |  | User
| Test syntax |  |  |  | External Component (specify)
| Test logic |  |  | Op Spec type | User
| Test interface |  |  |  | Interface
Test checking
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Metaphysics: | Object-oriented
Functional
Sizes: | VS
S
M
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
| Estimated |  |  |  |  | Actual
Base Components | Base LOC | Deleted LOC | Modified LOC | Added LOC |  | Base LOC | Deleted LOC | Modified LOC | Added LOC
Totals | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Estimated |  |  |  |  | Actual
New Components | Method Count | Rel Size | LOCr | Reuseable? |  | Method Count | LOCa | Reusable?
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Totals |  |  | 0 | 0 |  |  | 0 | 0
| Estimated | Actual
Reused Parts | LOC | LOC
Totals | 0 | 0
Size Calculation
| LOCr= |  | 0
| sum(LOCa)/sum(LOCr)= |  | 0
| LOCp= |  | 0
| confidence= |  | 0 | Low
Effort Calculation
Productivity=
| sum(Ea)/sum(LOCa)= |  | 0
| Ep= |  | 0
| LPI= |  | 0
| UPI= |  | 0
| confidence= |  | 0 | Low
Estimation Override | LOCp= |  | 0
| Ep= |  | 0
Rationale for override:

## Plan
Constants |  |  |  |  | Assignment 2
Start date: | 36526 |  | Grades: | AA | 1
End date: | 73051 |  |  | A | 0.95
Phases: | Analysis |  |  | AB | 0.9
| Architecture |  |  | B | 0.85
| Project planning |  |  | BC | 0.8
| Interation planning |  |  | C | 0.75
| Construction |  |  | CD | 0.7
| Refactoring |  |  | D | 0.65
| Review |  |  | F | 0.5
Integration test
Repatterning
Postmortem
Sandbox
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful
| Test syntax | Syntax flaws in the test code |  | 6
| Test logic | Logic flaws in the test code |  | 7
| Test interface | Flaws in the interface of a component of the test code |  | 8
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0
Y/N: | Yes |  |  | Passed | 0
| No |  |  | Passed with issues | 0
Proxy Types: | - |  |  | Failed
| Calculation |  |  | Not tested
| Data |  |  | Not applicable
I/O
Logic
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
| 0 | 0 | 0 | 0
<-- Mandatory |  | ✔
Project Plan Summary
Use this worksheet to record how much production code you plan to write and the amount of time to write it. Record the actual size once the project is complete. The actual time will be calculated from the Time Log. Please note that you are not being evaluated on how close your planned values to your actual values.
Program Size (LOC) |  | Plan | Actual | To Date
Base code LOC count |  |  |  | 0
Lines deleted from Base |  |  |  | 0
Lines modified from Base |  |  |  | 0
Lines added to Base |  |  |  | 0
Reused lines |  |  |  | 0
New lines of production code |  | 75 | 24 | 24
Component Count |  | Plan | Actual | To Date
Reused components |  |  |  | 0
Modified components |  |  |  | 0
New components |  |  |  | 0
Time In Phase (minutes) |  | Plan | Actual | Actual to Date | Actual to Date %
Analysis |  | 0 | 40 | 40 | 13.79%
Architecture |  | 0 | 0 | 0 | 0%
Project planning |  | 0 | 0 | 0 | 0%
Interation planning |  | 0 | 0 | 0 | 0%
Construction |  | 0 | 195 | 195 | 67.24%
Refactoring |  | 0 | 0 | 0 | 0%
Review |  | 0 | 0 | 0 | 0%
Integration test |  | 0 | 0 | 0 | 0%
Repatterning |  | 0 | 30 | 30 | 10.34%
Postmortem |  | 0 | 25 | 25 | 8.621%
Sandbox |  | 0 | 0 | 0 | 0%
TOTAL |  | 240 | 290 | 290 | 100%
Changes Identified |  |  | Actual | Actual to Date | Actual to Date %
Analysis |  |  | 0 | 0 | 0%
Architecture |  |  | 0 | 0 | 0%
Project planning |  |  | 0 | 0 | 0%
Interation planning |  |  | 0 | 0 | 0%
Construction |  |  | 5 | 5 | 100%
Refactoring |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repatterning |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 5 | 5 | 100%
Changes Implemented |  |  | Actual | Actual to Date | Actual to Date %
Analysis |  |  | 0 | 0 | 0%
Architecture |  |  | 0 | 0 | 0%
Project planning |  |  | 0 | 0 | 0%
Interation planning |  |  | 0 | 0 | 0%
Construction |  |  | 5 | 5 | 100%
Refactoring |  |  | 0 | 0 | 0%
Review |  |  | 0 | 0 | 0%
Integration test |  |  | 0 | 0 | 0%
Repatterning |  |  | 0 | 0 | 0%
Postmortem |  |  | 0 | 0 | 0%
Sandbox |  |  | 0 | 0 | 0%
TOTAL |  |  | 5 | 5 | 100%
Note on C48: Number of lines used from previously-written code
Note on C49: Estimate of the number of lines deleted from previously-written code
Note on C50: Estimated of the number of lines modified from previously-written code
Note on C51: Estimate of the number of lines added to previously-written code to bring it to the point where new functionality can be added
Note on C52: Count of the number of lines of reused source code
Note on C53: Estimate the number of new lines of production code that provide new functionality to meet the specifications of this assignment.
Note on C56: Number of reusable components that will be reused.
Note on C57: Estimate of the number of previously-delivered components that will be used.
Note on C58: Estimate of the number of new components to be built.
Note on C72: Estimate in minutes how much time you plan to expend on this assignment.

## Iterations (hidden)
Iterations
Standards
Start date: | 2000-01-01
End date: | 2025-01-01
Phases: | Planning
Design
Design Review
Code
Code Review
Compile
Test
Postmortem
Documentation
Syntax
Defect Types: | Build, Package
Assignment
Interface
Checking
Data
Function
System
Environment
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
|  |  | estimation methods | A
Sizes: | VS |  |  | B
| S |  |  | C
| M |  |  | D
L
VL
Duration: | LOCe x T
LOCa x T
Productivity
Component-Iteration Map
| Component | Iteration 1 | Iteration 2 | Iteration 3 | Iteration 4 | Iteration 5 | Iteration 6 | Iteration 7 | Iteration 8 | Iteration 9 | Iteration 10
Base Components | [11 empty] | 0
0
0
0
0
0
0
0
0
0
New Components | [11 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| Number of tasks: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Effort: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
WBS
| Iteration Number | Planned Effort (minutes) | Cumulative Planned Effort | Planned Velocity | Cumulative Planned Velocity | Planned Completion Date
| 1 |  | 0 |  | 0
| 2 |  | 0 |  | 0
| 3 |  | 0 |  | 0
| 4 |  | 0 |  | 0
| 5 |  | 0 |  | 0
| 6 |  | 0 |  | 0
| 7 |  | 0 |  | 0
| 8 |  | 0 |  | 0
| 9 |  | 0 |  | 0
| 10 |  | 0 |  | 0
Calendar
| Day # | Date | Available Minutes | Cumulative Minutes | Planned Velocity | Cumulative Planned Velocity
| 1 | due date - 24 |  | 0 |  | 0
| 2 | due date - 23 |  | 0 |  | 0
| 3 | due date - 22 |  | 0 |  | 0
| 4 | due date - 21 |  | 0 |  | 0
| 5 | due date - 20 |  | 0 |  | 0
| 6 | due date - 19 |  | 0 |  | 0
| 7 | due date - 18 |  | 0 |  | 0
| 8 | due date - 17 |  | 0 |  | 0
| 9 | due date - 16 |  | 0 |  | 0
| 10 | due date - 15 |  | 0 |  | 0
| 11 | due date - 14 |  | 0 |  | 0
| 12 | due date - 13 |  | 0 |  | 0
| 13 | due date - 12 |  | 0 |  | 0
| 14 | due date - 11 |  | 0 |  | 0
| 15 | due date - 10 |  | 0 |  | 0
| 16 | due date - 9 |  | 0 |  | 0
| 17 | due date - 8 |  | 0 |  | 0
| 18 | due date - 7 |  | 0 |  | 0
| 19 | due date - 6 |  | 0 |  | 0
| 20 | due date - 5 |  | 0 |  | 0
| 21 | due date - 4 |  | 0 |  | 0
| 22 | due date - 3 |  | 0 |  | 0
| 23 | due date - 2 |  | 0 |  | 0
| 24 | due date - 1 |  | 0 |  | 0
| 25 | due date |  | 0 |  | 0
| 26 | due date + 1 |  | 0 |  | 0
| 27 | due date + 2 |  | 0 |  | 0
| 28 | due date + 3 |  | 0 |  | 0
| 29 | due date + 4 |  | 0 |  | 0
| 30 | due date + 5 |  | 0 |  | 0
| 31 | due date + 6 |  | 0 |  | 0
| 32 | due date + 7 |  | 0 |  | 0
| 33 | due date + 8 |  | 0 |  | 0
| 34 | due date + 9 |  | 0 |  | 0
| 35 | due date + 10 |  | 0 |  | 0
| 36 | due date + 11 |  | 0 |  | 0
| 37 | due date + 12 |  | 0 |  | 0
| 38 | due date + 13 |  | 0 |  | 0
| 39 | due date + 14 |  | 0 |  | 0
| 40 | due date + 15 |  | 0 |  | 0
| 41 | due date + 16 |  | 0 |  | 0
| 42 | due date + 17 |  | 0 |  | 0

## PlanSummary (hidden)
Project Plan Summary
Standards
Start date: | 2000-01-01 |  | Grades: | AA
End date: | 40179 |  |  | A
Phases: | Analysis |  |  | AB
| Architecture |  |  | B
| Planning |  |  | BC
| Construction |  |  | C
| Refactoring |  |  | CD
| Review |  |  | D
| Integration Test |  |  | F
Postmortem
Sandbox
Defect Types: | Documentation |  | Iteration | NA
| Build |  |  | 1
| Product syntax |  |  | 2
| Product logic |  |  | 3
| Product interface |  |  | 4
| Product checking |  |  | 5
| Test syntax |  |  | 6
| Test logic |  |  | 7
| Test interface |  |  | 8
| Test checking |  |  | 9
| Bad Smell |  |  | 10
Y/N: | Yes
No
Proxy Types: | Calculation
Data
I/O
Logic
Sizes: | VS
S
M
L
VL
|  | Plan | Actual | To Date
Program Size (LOC)
Base code LOC count |  | 0 | 0 | 0
Lines deleted from Base |  | 0 | 0 | 0
Lines modified from Base |  | 0 | 0 | 0
Lines added to Base |  | 0 | 0 | 0
Reused lines |  | 0 | 0 | 0
New lines of production code |  | 0 | 0 | 0
|  | Plan | Actual | To Date | To Date %
Time In Phase (minutes)
Analysis |  | 0 | 40 | 40 | 160%
Architecture |  | 0 | 0 | 0 | 0%
Project planning |  | 0 | 0 | 0 | 0%
Interation planning |  | 0 | 0 | 0 | 0%
Construction |  | 0 | 195 | 195 | 780%
Refactoring |  | 0 | 0 | 0 | 0%
Review |  | 0 | 0 | 0 | 0%
Integration test |  | 0 | 0 | 0 | 0%
Repatterning |  | 0 | 30 | 30 | 120%
Postmortem |  | 0 | 25 | 25 | 100%
Sandbox |  | 0 | 0 | 0 | 0%
TOTAL |  | 0 | 290 | 290 | 1160%
Changes traced to
Analysis |  |  | 0 | 0
Architecture |  |  | 0 | 0
Project planning |  |  | 0 | 0
Interation planning |  |  | 0 | 0
Construction |  |  | 1 | 1
Refactoring |  |  | 0 | 0
Review |  |  | 0 | 0
Integration test |  |  | 0 | 0
Repatterning |  |  | 0 | 0
Postmortem |  |  | 0 | 0
Sandbox |  |  | 0 | 0
TOTAL |  |  | 1 | 1
Changes implemented in
Analysis |  |  | 0 | 0
Architecture |  |  | 0 | 0
Project planning |  |  | 0 | 0
Interation planning |  |  | 0 | 0
Construction |  |  | 1 | 1
Refactoring |  |  | 0 | 0
Review |  |  | 0 | 0
Integration test |  |  | 0 | 0
Repatterning |  |  | 0 | 0
Postmortem |  |  | 0 | 0
Sandbox |  |  | 0 | 0
TOTAL |  |  | 1 | 1

## Change Log
Constants |  |  |  |  | Assignment 2
Start date: | 36526 |  | Grades: | AA | 1 | 0 | 43369 | 0
End date: | 73051 |  |  | A | 0.95 | 0 | 0 | 0
Phases: | Analysis |  |  | AB | 0.9 | 0 | 0 | 0
| Architecture |  |  | B | 0.85 | 0 | 0 | 0
| Project planning |  |  | BC | 0.8 | 0 | 0 | 0
| Interation planning |  |  | C | 0.75 | 0 | 0 | 0
| Construction |  |  | CD | 0.7 | 43360 | 1 | 0
| Refactoring |  |  | D | 0.65 | 43361 | 2 | 5
| Review |  |  | F | 0.5 | 43362 | 3 | 10
| Integration test |  |  |  |  | 43363 | 4 | 15
| Repatterning |  |  |  |  | 43364 | 5 | 20
| Postmortem |  |  |  |  | 43365 | 6 | 25
| Sandbox |  |  |  |  | 43366 | 7 | 30
| Previous Project |  |  |  |  | 43367 | 8 | 35
[6 empty] | 43368 | 9 | 40
[6 empty] | 43369 | 10 | 45
[6 empty] | 43370 | 11 | 50
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | 43371 | 12 | 55
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | 43372 | 13 | 0
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | 43373 | 14 | 0
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | 43374 | 15 | 0
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | 43375 | 16 | 0
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | 43376 | 17 | 0
| Test syntax | Syntax flaws in the test code |  | 6 |  | 43377 | 18 | 0
| Test logic | Logic flaws in the test code |  | 7 |  | 43378 | 19 | 0
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | 43379 | 20 | 0
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | 43380 | 21 | 0
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 | 0 | 43381 | 22 | 0
Y/N: | Yes |  |  | Passed | 0 | 43382 | 23 | 0
| No |  |  | Passed with issues | 0 | 43383 | 0 | 0
Proxy Types: | - |  |  | Failed |  | 43384 | 0 | 0
| Calculation |  |  | Not tested |  | 43385 | 0 | 0
| Data |  |  | Not applicable |  | 43386 | 0 | 0
| I/O |  |  |  |  | 43387 | 0 | 0
| Logic |  |  |  |  | 43388 | 0 | 0
[6 empty] | 43389 | 0 | 0
Sizes: | VS | S | M | L | VL | 0 | 0 | 0
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999 | 0 | 0 | 0
mid | -2 | -1 | 0 | 1 | 2 | 0 | 0 | 0
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5 | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0
[6 empty] | 0 | 0 | 0
<-- Mandatory |  | ✔ |  |  |  | 0 | 0 | 0
Change Log
Use this worksheet to record changes to made to artifacts after the project is underway. Record repairs to defects, as well as changes that result from requirements clarifications/changes.
|  | Change Designation | Description
|  | Requirements Change | Changes to requirements
|  | Requirements Clarification | Clarifications to requirements
|  | Product syntax | Syntax flaws in the deliverable product
|  | Product logic | Logic flaws in the deliverable product
|  | Product interface | Flaws in the interface of a component of the deliverable product
|  | Product checking | Flaws with boundary/type checking within a component of the deliverable product
|  | Test syntax | Syntax flaws in the test code
|  | Test logic | Logic flaws in the test code
|  | Test interface | Flaws in the interface of a component of the test code
|  | Test checking | Flaws with boundary/type checking within a component of the test code
|  | Bad Smell | Refactoring changes (please note the bad smell in the defect description)
Change Number | Date Of Change | Change Type | Activity Where Injected | Interation Where Injected | Activity Where Removed | Iteration Where Removed | Fix Time | Reference To A Previous Change | Description
1 | 2018-09-24 | Product logic | Construction | NA | Construction | NA | 5 |  | Forgot that the keyset of a dict in python cannot be used as an ordered list
2 | 2018-09-24 | Test logic | Construction | NA | Construction | NA | 2 |  | Failed to realize that a red light test doesn't break the current product logic
3 | 2018-09-24 | Test logic | Construction | NA | Construction | NA | 3 |  | Made the specified value = default value by mistake on a sad path test
4 | 2018-09-24 | Test logic | Construction | NA | Construction | NA | 10 |  | Neglected to change format of createCubeTest tests after refactoring createCube
5 | 2018-09-25 | Product logic | Construction | NA | Construction | NA | 3 |  | Forgot to click Red Light, but Test for invalid face key passed unintentionally because of existing production code
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75

## Time Log
Constants | [6 empty] | Assignment 2
Start date: | 36526 |  | AA |  | Grades: | AA | 1
End date: | 73051 |  | A |  |  | A | 0.95
Phases: | Analysis |  | AB |  |  | AB | 0.9
| Architecture |  | B |  |  | B | 0.85
| Project planning |  | BC |  |  | BC | 0.8
| Interation planning |  | C |  |  | C | 0.75
| Construction |  | CD |  |  | CD | 0.7
| Refactoring |  | D |  |  | D | 0.65
| Review |  | F |  |  | F | 0.5
Integration test
Repatterning
Postmortem
Sandbox
Defect Types: | Requirements Change |  | NA |  | Iteration | NA | did not follow
| Requirements Clarification |  | 1 |  |  | 1 | very painful
| Product syntax |  | 2 |  |  | 2 | painful
| Product logic |  | 3 |  |  | 3 | neutral
| Product interface |  | 4 |  |  | 4 | helpful
| Product checking |  | 5 |  |  | 5 | very helpful
| Test syntax |  | 6 |  |  | 6
| Test logic |  | 7 |  |  | 7
| Test interface |  | 8 |  |  | 8
| Test checking |  | 9 |  |  | 9
| Bad Smell |  | 10 |  |  | 10 | 0
Y/N: | Yes |  | Passed |  |  | Passed | 0
| No |  | Passed with issues |  |  | Passed with issues | 0
Proxy Types: | - |  | Failed |  |  | Failed
| Calculation |  | Not tested |  |  | Not tested
| Data |  | Not applicable |  |  | Not applicable
I/O
Logic
Sizes: | VS |  | L |  | M | L | VL
upper | -1.5 |  | 1.5 |  | 0.5 | 1.5 | 99999
mid | -2 |  | 1 |  | 0 | 1 | 2
lower | 0 |  | 0.5 |  | -0.5 | 0.5 | 1.5
| 0 |  | 0 |  | 0 | 0
<-- Mandatory
Time Recording Log
Use this worksheet to record the amount of time you spend on each activity. Use the "sandbox" activity to record time spent experimenting with the assignment requirements..
Activity
Analysis
Architecture
Project planning
Interation planning
Construction
Refactoring
Review
Integration test
Repatterning
Postmortem
Sandbox
| Start Time |  | Stop Time
Date | Hour | Min | Hour | Min | Interrupt | Delta | Activity | Iteration | Comments
2018-09-24 | 15 | 30 | 15 | 45 |  | 15 | Analysis |  | Mostly creating and formatting analysis for dispath -- op=create
2018-09-24 | 15 | 45 | 16 | 5 |  | 20 | Construction
2018-09-24 | 16 | 10 | 16 | 40 | 5 | 25 | Analysis |  | Setting up CubeCreateTest and formatting analysis
2018-09-24 | 16 | 40 | 18 | 0 | 10 | 70 | Construction |  | Building createCube
2018-09-24 | 19 | 50 | 20 | 50 |  | 60 | Construction |  | Updated input verification and refactored createCube
2018-09-25 | 20 | 50 | 21 | 40 | 5 | 45 | Construction
2018-09-25 | 21 | 45 | 22 | 15 |  | 30 | Repatterning
2018-09-25 | 22 | 15 | 22 | 40 |  | 25 | Postmortem

## Lessons
Lessons Learned
Problems of Importance
1
2
3
4
5
Proposal for Improvements
1
2
3
4
5
Notes and Comments
1
2
3
4
5

## Coding Standard
Coding Standard
A coding standard provides a map so that the code generated by a group of programmers will be consistent and, therefore, easier to read and maintain.
File headings
Place a doc string at the beginning of each file. The doc string should state the purpose of the file's contents, the date the file was baselined, the date of any modifications subsequent to being baselined, and the name of the author. Each line of the doc string should be indented by four spaces. It can be delimited by either three double quotes or three single quotes. [Rationale: This provides identifying information for the file.]
Example
'''
Created on Aug 27, 2018
@author: David Umphress
'''
Use of docstrings elsewhere is optional. If used, they may be free form; i.e., this coding standard specifies no format.
Comments
Use # for comments other than doc strings. [Rationale: This style of commenting makes comments consistent across other programming languages.]
Example
# Return the answer to the universe
return 42
Do not include comments such as "#end if" to denote end of structural constructs. [Rationale: Indentation gives a visual cue to nesting; comments that indicate end of blocks of code decrease readability.]
Multiple assignment statements
Avoid multiple assignment statements. Use only in situations where readability would be significantly affected by using single assignment statements. [Rationale: Multiple logical lines per physical line result in an inaccurate LOC count.]
|  | Not OK | OK
|  | myVar1, myVar2 = 0, 1 | myVar1 = 0
myVar2 = 1
|  | import os, sys | import os
import sys
Spanning physical lines
Logical lines can span multiple physical lines. In such cases, the continuation lines must be indented one indentation beyond the initial line. Break lines after operators or commas. [Rationale: Indentation improves readability.]
Do not span strings over more than one physical line. In cases where a string won’t fit on a physical line, break the string into individual parts that will fit on a line and concatenate the parts. [Rationale: This simplifies construction of tools that count lines of code.]
|  | Not OK | OK
|  | myVar1 = myVar2 + myVar3 + \ | myVar1 = myVar2 + myVar3 + \
|  | myVar4 | myVar4;
|  | myString = '''multi-line | myString='multi-line ’ + \
|  | string''' | ‘string’
Blank lines
Use blank lines to break up related chunks of code. Use at least one blank line between all methods. [Rationale: Blank lines visually segment blocks of related code, thus making it more understandable.]
Code readability
Code should be as self-documenting as possible. For example:
· Identifiers should be given meaningful names that indicate purpose or use.
· Single letters should only be used as names for loop indices when mirroring a mathematical equation specified in the requirements, otherwise, loop indices should be given names that indicate their use.
· Magic numbers – meaning, numbers that appear without explanation in source code – are to be avoided. If they appear, they should be assigned to identifiers that describe their purpose.
· Comments should be used sparingly as an aid to understanding non-intuitive code structure, complex calculations, unique circumstances, etc. It should not be a substitute for unreadable code.
[Rationale: These practices improve comprehension of code.]
Identifier naming
Variables should follow a camel-case convention (i.e., the identifier consists of a series of words with the spaces removed; the beginning letter should be lower case; the beginning letter of each word should be uppercase.)
Class names should be nouns in camel-case, with the first letter capitalized.
Example
class MyClass
Function names and method names should be in camel-case, with the first letter in lower case. The name should connote action and thus should be a verb or verb phrase.
Example
def run()
def getValue()
Methods that retrieve a Boolean object state must use the prefix is in the method name.
Example
isEnabled()
Identifiers designated to be constant should be nouns in all upper case with words separated by an underscore. All other identifiers should be nouns in camel-case, with the first letter in lower case.
Multiple inheritance
Do not use multiple inheritance. [Rationale: This practice decreases understandability.]
File structure
Code should be developed in your IDE using a directory/file structure along the lines of the following:
Note that we differentiating “production” code from “test” code. The former fulfulls requirements and the latter verifies that the requirements are fulfilled. “Sandbox” code is code used to experiment with concepts or programming language constructs. It is not to be used to develop production code.
File contents
Unless specified otherwise, each class should be stored in its own file. The name of the file should be the name of the class followed by a “.py” extension. For example, class “MyComponent” should be located in a file named “MyComponent.py”.
Test code should be placed in a file whose file name clearly reflects what component is being tested. In most cases, the file name will be the component name appended with “Test.py”. For example, “MyComponentTest.py” would contain the code that tests “MyComponent.py”.

## Counting Standard
Counting Standard
A counting standard defines how to determine the number of lines of code.
Each non-blank, non-comment, non-doc string line of production code counts as one line of code.
Example:
| ''' | doc string … not a line of code
| Created to demonstrate the counting standard | doc string … not a line of code
| Baselined: 1 Aug 2016 | doc string … not a line of code
| Modified: 29 Sep 2016 | doc string … not a line of code
| @author: D. Umphress | doc string … not a line of code
| ''' | doc string … not a line of code
| import something | line of code
blank line … not a line of code
| def fib(n): | line of code
| ''' fib(n) calculates the Fibbanacci value of n ''' | doc string … not a line of code
| prev = 0 | line of code
| next = 1 | line of code
blank line … not a line of code
| for i in range(n - 1): | line of code
| temp = next | line of code
| next = next + prev | line of code
| prev = temp | line of code
| return next | line of code
total lines of code in the file: 9
total number of components: 1
name: fib
component method count = 1
component LOC count= 8

## Source (hidden)
Source Code
Paste production source code here. (1) copy your code to the clipboard, (2) click on the "PASTE ME" cell (not the entire row), (3) paste. Do not paste test code.
PASTE ME

## Constants (hidden)
Constants |  |  |  |  | Assignment 2
Start date: | 2000-01-01 |  | Grades: | AA | 100% |  | 2018-09-26
End date: | 2100-01-01 |  |  | A | 95%
Phases: | Analysis |  |  | AB | 90%
| Architecture |  |  | B | 85%
| Project planning |  |  | BC | 80%
| Interation planning |  |  | C | 75%
| Construction |  |  | CD | 70% | 2018-09-17 | 1 | 0 | AM
| Refactoring |  |  | D | 65% | 2018-09-18 | 2 | 5 | PM
| Review |  |  | F | 50% | 2018-09-19 | 3 | 10
| Integration test |  |  |  |  | 2018-09-20 | 4 | 15
| Repatterning |  |  |  |  | 2018-09-21 | 5 | 20
| Postmortem |  |  |  |  | 2018-09-22 | 6 | 25
| Sandbox |  |  |  |  | 2018-09-23 | 7 | 30
[6 empty] | 2018-09-24 | 8 | 35
[6 empty] | 2018-09-25 | 9 | 40
[6 empty] | 2018-09-26 | 10 | 45
[6 empty] | 2018-09-27 | 11 | 50
Defect Types: | Requirements Change | Changes to requirements | Iteration | NA | did not follow | 2018-09-28 | 12 | 55
| Requirements Clarification | Clarifications to requirements |  | 1 | very painful | 2018-09-29 | 13
| Product syntax | Syntax flaws in the deliverable product |  | 2 | painful | 2018-09-30 | 14
| Product logic | Logic flaws in the deliverable product |  | 3 | neutral | 2018-10-01 | 15
| Product interface | Flaws in the interface of a component of the deliverable product |  | 4 | helpful | 2018-10-02 | 16
| Product checking | Flaws with boundary/type checking within a component of the deliverable product |  | 5 | very helpful | 2018-10-03 | 17
| Test syntax | Syntax flaws in the test code |  | 6 |  | 2018-10-04 | 18
| Test logic | Logic flaws in the test code |  | 7 |  | 2018-10-05 | 19
| Test interface | Flaws in the interface of a component of the test code |  | 8 |  | 2018-10-06 | 20
| Test checking | Flaws with boundary/type checking within a component of the test code |  | 9 |  | 2018-10-07 | 21
| Bad Smell | Refactoring changes (please note the bad smell in the defect description) |  | 10 |  | 2018-10-08 | 22
Y/N: | Yes |  |  | Passed |  | 2018-10-09 | 23
| No |  |  | Passed with issues |  | 2018-10-10
Proxy Types: | - |  |  | Failed |  | 2018-10-11
| Calculation |  |  | Not tested |  | 2018-10-12
| Data |  |  | Not applicable |  | 2018-10-13
| I/O |  |  |  |  | 2018-10-14
| Logic |  |  |  |  | 2018-10-15
2018-10-16
Sizes: | VS | S | M | L | VL
upper | -1.5 | -0.5 | 0.5 | 1.5 | 99999
mid | -2 | -1 | 0 | 1 | 2
lower | 0 | -1.5 | -0.5 | 0.5 | 1.5
<-- Mandatory |  | ✔